## Sheet1
INFO6090 Weekly Team Meeting Progress and Planning Sheet
Team: | GroupH |  |  | Member ID | Members(given, Family Name) |  |  |  |  | Members Present (ID)
|  |  |  | 1 | Le Duc Anh Nguyen |  |  |  |  | C3445530
Semester Week: | week9 |  |  | 2 | Wenjuan Ma |  |  |  |  | C3415026
|  |  |  | 3 | Quang Hoang |  |  |  |  | C3468884
q
Task ID (keep old ID's) | Task Description |  |  | Members Assigned (IDs) | Estimated Completion Date | Work In Progress (WIP) Due Date(s) | Work in Progress Uploaded Status | Task Status | Comments
1 | assignment request analysis |  |  | all of the members | week9 | week10 | yes | Completed | check all of the detail about the case and request of assignments.
2 | Data Model Design |  |  | C3415026 | week9 | week10 | yes | Completed | designing the draft of "Sales" Star DataMart
3 | Definition of Fact Table and Dimension Tables |  |  | C3415026 | week9 | week10 | yes | Completed | define entity-relationship diagrams, attribute definitions.
4 | Design Justifications & Correctness |  |  | C3415026 | week9 | week10 | yes | Completed
INFO6090 Weekly Team Meeting Progress and Planning Sheet
Team: | GroupH |  |  | Member ID | Members(given, Family Name) |  |  |  |  | Members Present (ID)
|  |  |  | 1 | Le Duc Anh Nguyen |  |  |  |  | C3445530
Semester Week: | week10 |  |  | 2 | Wenjuan Ma |  |  |  |  | C3415026
|  |  |  | 3 | Quang Hoang |  |  |  |  | C3468884
q
Task ID (keep old ID's) | Task Description |  |  | Members Assigned (IDs) | Estimated Completion Date | Work In Progress (WIP) Due Date(s) | Work in Progress Uploaded Status | Task Status | Comments
1 | ETL/ELT Process Overview |  |  | C3415026 | week10 | week11 | Yes | Completed | Outline the Extract, Transform, Load (ETL) . Describe source data, data cleansing, transformation steps, and loading into the DataMart.
2 | SQL Scripts to Clean Data |  |  | C3415026 | week10 | week11 | Yes | Completed
3 | Load scripts/processes to populate Data Mart |  |  | C3415026 | week10 | week11 | Yes | Completed
INFO6090 Weekly Team Meeting Progress and Planning Sheet
Team: | GroupH |  |  | Member ID | Members(given, Family Name) |  |  |  |  | Members Present (ID)
|  |  |  | 1 | Le Duc Anh Nguyen |  |  |  |  | C3445530
Semester Week: | week11 |  |  | 2 | Wenjuan Ma |  |  |  |  | C3415026
|  |  |  | 3 | Quang Hoang |  |  |  |  | C3468884
q
Task ID (keep old ID's) | Task Description |  |  | Members Assigned (IDs) | Estimated Completion Date | Work In Progress (WIP) Due Date(s) | Work in Progress Uploaded Status | Task Status | Comments
1 | Original data issues and SQL descriptions for reporting |  |  | C3468884 | WEEK11 | WEEK12 | No | Completed
2 | Insight & Reporting analysis |  |  | C3468884 | WEEK11 | WEEK12 | Yes | Completed | Present raw results of the analysis, including data tables, charts, and key findings that form the basis for recommendations.
INFO6090 Weekly Team Meeting Progress and Planning Sheet
Team: | GroupH |  |  | Member ID | Members(given, Family Name) |  |  |  |  | Members Present (ID)
|  |  |  | 1 | Le Duc Anh Nguyen |  |  |  |  | C3445530
Semester Week: | week12 |  |  | 2 | Wenjuan Ma |  |  |  |  | C3415026
|  |  |  | 3 | Quang Hoang |  |  |  |  | C3468884
Task ID (keep old ID's) | Task Description |  |  | Members Assigned (IDs) | Estimated Completion Date | Work In Progress (WIP) Due Date(s) | Work in Progress Uploaded Status | Task Status | Comments
1 | Data anomallies and SQL descriptions for reporting |  |  | C3445530, C3468884 | WEEK12 | WEEK12 | Yes | Completed
2 | Insight & Reporting analysis |  |  | C3445530 | WEEK12 | WEEK12 | Yes | Completed | Present raw results of the analysis, including data tables, charts, and key findings that form the basis for recommendations.
3 | Business Recommendations |  |  | C3445530 | WEEK12 | WEEK12 | Yes | Completed | Summarize recommendations for the business based on the analysis results, supported by evidence from the analysis.
4 | Suggestion for the business plan |  |  | C3445530 | WEEK12 | WEEK12 | Yes | Completed | Further suggestion for business plan
5 | Dashboard |  |  | C3445530 | WEEK12 | WEEK12 | Yes | Completed
6 | Conclusion |  |  | C3415026 | WEEK12 | WEEK12 | Yes | Completed | Conclusion of the report
Legend
Task ID: |  | Each task is to have a unique ID (the ID is repeated weekly until the task is reviewed, accepted and markeked as completed)
WIP Uploaded Status: |  | Yes, No
Task Status: |  | Completed, In Porgress, in Review, Reassigned to (member IDs)